## Project Info
Project Summary | The primary objective of the project is to revamp the existing web application ecosystem in a way that is visually appealing, uniform inflow, and provides ease of access. The budget approved for the infrastructure upgrade is $120,000 and the web implementation should be completed within 7 months. The goal is to implement a single sign-on to log into multiple web applications and develop an authentication system that is similar to the one used for accessing official email accounts within the organization. UI needs to be uniform in design and the application should be compatible with mobile devices for quick approvals and feedback from the leadership. We need to create an integrated and uniform web application that will act as a single point of contact for a wide range of services offered by Mustang Banking along with the employees’ performance dashboard. The web application will authenticate the user using a single sign-on which can be done either using a verification code sent via email/text or by using an employee code and password. The application will have a mobile-first responsive design to speed up the approval process and, therefore, improve turnaround times.
Communication Plan Purpose | The purpose of the communication plan is to effectively manage the flow of information throughout the program including both internal communication and communication with the client. In order to effectively complete the project scope at the desired quality within the specified time and scope constraints of the project, it is imperative to ensure that all necessary information is conveyed to the correct party in a timely manner.
Communication Plan Objectives | The objective of this document is to provide clear instructions for all members of the project on how to communicate. This includes but is not limited to communication roles, communication channels, and how to use them. Additionally, this document will clearly describe how project members are expected to communicate within the project and the escalation process.

## Modes of Communication
# | Mode of Communication | Category | Cadence | Usage Explanation
1 | Formal Meeting | Interactive | Daily | The meetings will be required to provide status update, cover road blocks and review future plans
2 | Casual Meeting | Interactive | Ad hoc | To discuss small speed breakers and issues that requires short and quick attention
3 | Email | Interactive | Daily+Ad hoc | Will be used to send out summary of daily tasks, answers to key question and plan for tomorrow
4 | Instant Messaging | Interactive/Push | Ad hoc | To discuss small speed breakers and issues that requires short and quick attention, reach out for small confirmations
5 | Video Call | Interactive | Bi-Monthly | In order to keep in touch with client and associate names with the face, understand and analyse visual cues to better communicate client
6 | Phone | Interactive/Push | Weekly, Ad hoc | Used to communicate with the client/on-shore team, reached remotely working team members
7 | Meeting Notes | Push | Daily | In order to ensure all the stakeholders are on the same page and understand the work clearly
8 | Feedback Surveys | Pull | Ad hoc | Floated with the client and software users to better understand and record the issues of the people
9 | Share Training Material | Pull | Post module completion | To ensure that the users have a way to go back to learn the system again
10 | Voice Mail | Push | Ad hoc | To drop a quick note of confirmation/update to a stakeholder while they are not available immediately to talk to and do not have the facility to connect to the internet

## Stakeholder Information
Stakeholder Information and Communication Preferences
# | Group / Person | Role / Title | Concerns and Information Needs | Frequency of Communication | Communication Format / Channel | Notes
1 | Akshay Kulkarni | CEO | High level deliverables | Major Milestones | Progress/Timeline Update via emails | Provides approvals to official documents received and give required feedback
2 | Neeraj Mehta | Program Manager | Business needs and sprint tasks assignment | Weekly | Emails, Retrospective Meetings,, emails(CC), Weekly check-in meetings | Give approval to completed milestones and identify improvement areas
3 | Smriti Seth | Test Manager | Sprint tasks assignment | Daily | Daily stand-up meetings, retrospective meetings, project tracking software(JIRA), bug tracking Software(Zoho), emails(CC) | Approve Test cases for each sprint and assign use cases to test engineers.
4 | Anu Malhotra | Project Manager | Sprint tasks assignment | Daily | Daily stand-up meetings, retrospective meetings, project tracking software(JIRA), bug tracking Software(Zoho), emails | Go-to contact for questions regarding the deliverables and pulls in related people if necessary
5 | Deepak Bhardwaj | Software Developer | Technical needs of various modules | Daily | Daily stand-up meetings, retrospective meetings, project tracking software(JIRA), bug tracking Software(Zoho), emails | Go-to person for application related questions
6 | Ayush Rawlani | Test Engineer | Functional needs of various modules covered in sprint | Daily | Daily stand-up meetings, retrospective meetings, project tracking software(JIRA), bug tracking Software(Zoho), emails | Go-to person for test cases related questions

## Team Communication Plan
# | Communication type | Frequency | Participants | Deliverable | Description
1 | Meeting | Daily | All stake holders | Meeting notes | The meetings will be required to provide status update, cover road blocks and review future plans
2 | Retrospective | Daily | All stake holders | Provide feedback, RCA and probable root cause analysis | A retrospective will provide feedback on the performance over the module, what issues were faced and how to be resolve
3 | Email | Daily+Ad hoc | All stake holders | Daily summary | Provide a summary of daily task via email, signoff on next day's plan and request clarification on topics
4 | Phone calls | Ad hoc | As required | Meeting notes | To be used while communicating with on-shore clients or remote working teammates
5 | Video Calls | Bi-Monthly | Client + Upper management | Meeting notes | To be used with client to provide visual cues and help them associate faces to names in emails, and voices on calls; build confidence
6 | Instant messaging | Ad hoc | As required | - | Instant messgaing to be used whenever you are required to have a quick solution to the small speedbreaker problems; not to be considered full and final
7 | Documentation | Ad hoc | All stake holders | Sign-off documents | To be used to provide all the stake holders a document to sign-off on project activities, acknowledgements and written confirmations

## Escalation Process
Escalation Process
Severity | Description | Decision Maker | Timeframe
High | Business and Mission critical applications are affected and/or not fuctioning as per the promised SLA's and require invocation of set Business Continuity and resiliency protocals protocols | CEO | Reponse time : less than 2 hours; Resolution Time : 1 Day
Medium | Business operations are impacted for a few consumers and internal workers | CTO / Project Manager | Reponse time : less than 6 hours; Resolution Time : 2 Days
Low | Internal workers are impacted with intermittent application disruptions. | Project Manager | Reponse time : less than 1 Day; Resolution Time : 1 week
Insignifcant | Application not functioning as required yet conceivable workaround is available and no business operations are impacted | Project Manager | Reponse time : less than 2 Days; Resolution Time : Based on priority and team backlog