## RACI Matrix
| RACI Matrix | Roles and Responsibilities
Responsible, Accountable, Consulted, Informed
|  | ROLES | Harsh Chaudhary (CEO) | Siddham Sharma (Project Manager) | Yash Katariya (Lead Developer) | Aaron Holle (Business Analyst) | Anu Malhotra (Test Manager) | Smrithi Seth (Software Developer 1) | Deepak Bhardwaj (Software Developer 2) | Dheeraj Mehta (Test Lead) | Neeraj Mehta (Test Engineer | Ayush Rawlani (Test Engineer)
| Deliverable or Task | Status | Sponsor | Project Team
Project Kick-Off
| Notice to proceed | Completed |  | R |  | D
| Interview team leads | Completed |  | R | C | D
| Interview Mustang Management | Completed |  | R |  | D
| Determine Final Budget | Completed |  | R | C | D
| Formal Budget Documentation and approval | Completed | R
| Collect Existing Documentation | Completed
| Conduct User Interviews | Completed |  | R | C | D
| Review Data Flows | Completed |  | R |  | D
| Document Necessary Applications | Completed |  | R |  | D
| Edit Documentation | Completed |  | R |  | D
| Create DFDs and Class Diagrams | Completed
| Consolidate Documentation in a single document | Completed |  | R
Project Phase 1
| Create User Stories | Completed |  |  | I | C | R
| Create Use Cases | Completed |  |  | I | C | R
| Finalize Requirements | Completed |  |  | I | C | R
| System Usage Analysis | Completed |  |  | I | C | R
| Vendor Selection | Completed |  |  | I | C | R
System Design Document
| Develop MVP | Completed |  | C |  | R | D
| Stake Holder Review | Completed |  | C |  | R | D
| Gather UAT Feedback | In progress |  |  |  | R |  |  |  | C |  | C
| Deployment | In progress |  |  |  | R
| Feedback Integraton | In progress |  |  |  | I
| Production Deployment | In progress |  |  |  | I |  |  |  | C
Project Phase 2
| Create User Stories | In progress |  |  |  | I |  |  |  | C |  | R
| Create Use Cases | Planned
| Develop Metrics | Planned | [7 empty] | A
| Finalize Requirements | Planned | [7 empty] | A
| System Usage Analysis | Planned | [7 empty] | I |  | R
| Vendor Selection | Planned | [7 empty] | I |  | R
| System Design Document | Planned | [7 empty] | I
| Develop MVP | Planned | [5 empty] | I |  | I |  | D
| Stake Holder Review | Planned | [7 empty] | I |  | D
| Gather UAT Feedback | Planned | [6 empty] | D | I
| Deployment | Planned | [6 empty] | R | I |  | C
| Feedback Integraton | Planned
| Production Deployment | Planned | [6 empty] | I | I
Project Phase 3
| Create User Stories | Planned | [6 empty] | A | I
| Create Use Cases | Planned
| Develop Metrics | Planned | [5 empty] | I |  | I |  | R
| Finalize Requirements | Planned |  | I | [5 empty] | I |  | R
| System Usage Analysis | Planned |  | I | [5 empty] | I | A | C
| Vendor Selection | Planned |  | R |  | I |  |  |  | I
| System Design Document | Planned
| Develop MVP | Planned |  | R |  | R | C |  | C
| Stake Holder Review | Planned | I | A | D | R
| Gather UAT Feedback | Planned |  | R
| Deployment | Planned |  | A |  | R
| Feedback Integraton | Planned | I | A |  | R
| Production Deployment | Planned |  | A |  | R
Project Handover and Closure
| Gauge Knowledge Level | Planned |  |  |  | I |  | I |  | R | R
| Conduct Interviews | Planned | I |  |  |  |  | I |  | R | R
| Group Employees for Training | Planned | I |  |  |  |  | I | A | C | C
| Define Knowledge Goals | Planned | R | I |  |  |  | I
| Write Curriculum for Groups | Planned
| Schedule Trainings | Planned
| Conduct Trainings | Planned
| Assess Learning | Planned | [8 empty] | I
| Additional Training | Planned
| Help Desk 1 | Planned |  |  | D | R |  |  | A
| Help Desk 2 | Planned |  |  |  | C | R |  |  | D
| Help Desk 3 | Planned | R |  | C | D | R
| Help Desk 4 | Planned
| Project Closure | Planned | I | D |  |  | R
D | Driver | Assists those who are responsible for a task.
R | Responsible | Assigned to complete the task or deliverable.
A | Accountable | Has final decision-making authority and accountability for completion. Only 1 per task.
S | Support | Provides support during implementation.
C | Consulted | An adviser, stakeholder, or subject matter expert who is consulted before a decision or action.
I | Informed | Must be informed after a decision or action.