## Risk Register
Project name: MUSTANG BANKING CONSOLIDATION PROJECT
Last Date Modified: November 14th 2021
Last Modified by: Harsh Chaudhari
Approver: Yash Katariya, Aaron Holle, Siddham Sharma
Risk Register ¦ Mustang Bank Consolidation Project
RISK # | DATE | UID | RISK | RISK CATEGORY | CONTROLS IN PLACE | OUTCOME RATING | LIKELIHOOD | RESPONSE SUMMARY | ACCOUNTABILITY
1 | 29/03/21 | R1.0 | Scope Creep in different domains/Modules during the consolidation project | Internal | 1) The client necessities are examined appropriately and reported with Interviews, JAD meetings, and Questionnaires 2) Expectations of the multitude of partners from project have been documented, scope and schedule is also formulated considering all the constraints. | 3 | 5 | 1) Involve a subset of clients in the second round of re-drafting the arrangement and examination records. 2) Set clear expectations and boundaries with the customers and partners and talk about what went in an unexpected way. 3) Check with the partners if the current tasks running amok is significant and if indeed, examine with the partners and undertaking individuals about conceivable timetable postponements | Project Manager/Project Sponsor
2 | 29/03/21 | R2.0 | Data/Network Security Breach | Technical | 1) All the servers and hubs are introduced with the fundamental organization safety efforts and firewalls to forestall any Distributed Denial of Service (DDoS) assaults or some other digital assaults 2) Prior quality affirmation and testing are done on all the organization hubs to check in case there are any escape clauses or weak rationale which may think twice about security of the organization | 4 | 2 | 1) The project undertaking is halted and all the security parameters are checked for the possible breach. 2) Rollback plan is devised and initiated if the breach is detected. 3) Setting up load balancer to manage the auto-failover and revive or replace a vulnerable node. | Network Engineer
3 | 29/04/21 | R3.0 | Actual and Approved Budget Discrepancy | Internal | 1) Estimates for every action in the Work Breakdown Chart are recomputed and reviewed to ensure that the actual financial plan lines up with the approved spending plan 2) Project Budget sheet is ready prior to beginning with the execution of the project and provisions are made for miscellaneous expenses. 3) The budget from each domain is gathered and checked with their separate partners to ensure that their viewpoint matches with others. | 4 | 3 | 1) The overall scope, budget plan, and schedule are re-assessed and reported back after completely dissecting the Work Breakdown Chart 2) The contrasts between the first spending plan and the new spending plan are examined and submitted to the survey board for verification and approval. 3) Once inspected, the new spending plan is introduced to the Project Sponsor and Stakeholder to review the feasibility of the project | Project Manager
4 | 30/05/21 | R4.0 | Physical Damage to Infrastructure/ Hardware Components | External | 1) Location of the actual equipment are ensured to be at secure spaces from any potential harm sources 2) Physical parameters (temperature, power, and so forth) are checked and reinforced before the execution. | 4 | 3 | 1) in the event of any actual harms to any/all equipment, the movement (in case proceeding) is made to stop and every one of the progressions are moved back to guarantee consistency 2) The root cause analysis is performed - in case it's interior or outer. If there's an occurrence of interior factors, the health check is performed to ensure smooth functioning. | Project Manager/Infrastructure and Middleware Team
5 | 30/05/21 | R5.0 | Training Delays | Internal | 1. Preplanned an customized trinaing curriculum to minimize confusion. 2. Detailed and easy to understand documentation to guide users through trainings. | 3 | 2 | 1. Convert some help desk resources into additional training resources if help desk is not needed/overstaffed. 2. If Help desk is also overrun during extended training period then as per direction of client either hire more temporary resources for training/help desk or extend the support period of the project. | Project Manger
6 | 19/04/21 | R6.0 | Physical component delivery delays. | External | 1. Built in lead time to insure that parts are on site before or exactly when they are needed for the project. 2. Plan for maximum acceptable delay without losing project efficiency by scheduling non-componenet dependent tasks. |  | 1 | 1. Shift efforts to task which do not alter the critical path and also do not require components. 2. Reevaluate critical path with delays calculated to ensure the remainder of the project is completed as smoothly as possible. | Product Owner
7 | 14/04/21 | R7.0 | Lack of executive dashboard acceptance | External | 1. Integrate executive feedback into all parts of dashboard design and development. 2. Rigourous testing and protytping to ensure design garners executive buy in. | 5 | 2 | 1. Immediately implement changes based on executive feedback. 2. Continue working, diregarding minor scope creep to ensure buy in from executive users.
8 | 14/04/21 | R8.0 | Sensitive Data Exposure | Technical | 1. Encrypting sensitive information being stored inside the application.2.Proper testing of the integrated application to identify vulnerabilities | 4 | 1 | 1) The module which exposed the sensitive data has to be modified. 2) New test cases has to be run on the software to eliminate future data exposure | Project Manager
9 | 14/04/21 | R9.0 | Unavailability of resources | Internal | 1. Clear layout of availability in advance for planned leaves 2. Appropriate knowledge transfer between resources so that work can be redistributed in events of unplanned leaves | 3 | 3 | 1. Realign on the tasks that were to be completed by the resource that’s unavailable. 2. Communicate to the same to the client in case of priorty tasks and timeline is affected 3. Check the impact of unavailability, reassess the current resource available and if required, plan for a new resource and onboarding process
10 | 14/04/21 | R10.0 | Change management | External | 1. The client goes through shift in business plans and asks us to pivot and make changes in our implementation | 4 | 1 | 1. Review the contract and the progress as per the project 2. Check the reusibility of the current modules in place 3. Estimate the changes required, update documentation, refloat change approvals 4. Create change management plan and resource requirement 5. Implement the changes
11 | 14/04/21 | R11.0 | Modules failures | Technical | 1. Test Cases to be pre-defined to ensure that the module is properly tested before UAT/deployment | 3 | 3 | 1. Evaluate the criticality of the module and the impact it makes 2. If not critical, deploy a hot fix and assume some techincal debt 3. If critical, do a RCA and decide upon the timeline to fix the module 4. Communicate the same to the client
12 | 14/04/21 | R12.0 | Gaps in understanding | Internal/External | 1. Create a communication plan for the users to ensure that everything is communicated properly | 4 | 4 | 1. Provided there are gaps in understanding the module, then send an email/document to confirm the understanding 2. Highlight places where the understanding differs and open a forum to clarify the doubts, follow up and get the changes approved 3. Once approved, document it in the repository and make changes in plans to communicate in future
13 | 14/04/21 | R13.0 | Stakeholder disapproval | External | 1. Identify the list of stakeholders and ensure that approvals are gathered ahead of time | 5 | 2 | 1. If a stakeholder disapproves any implementation, revisit the initial goal of the project 2. Allow the stakeholder to voice their approval, understand the pain points and check if the project goal allows the pain points to be resolved. 3. If so, log it as a change request, get the necessary approvals for the change, realign on those changes and implement them

## Legend
Risk Category | Outcome rating |  | Likelihood
Internal
External | 5 | Highest Impact | 5 | Most Likely to occur
Technical | 4 |  | 4
Unforseeable | 3 |  | 3
| 2 |  | 2
| 1 | Lowest Impact | 1 | Least likely to occur